## Projects
Projects | Type | Inc. in Demand | Priority
Mobile Banking App / New York | Mobile Application | Y | 1
Customer Portal / San Francisco | Web Application | Y | 2
Data Warehouse Migration / Chicago | Infrastructure | Y | 1
Analytics Dashboard / London | Data Analytics | Y | 3
Security Audit Tool / Berlin | Security | Y | 1
HR Portal Upgrade / Tokyo | Web Application | N | 2

## Project Roadmap
Projects | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11
Mobile Banking App / New York | BP | BP | BP | DEV | DEV | DEV | DEV | SIT | SIT | UAT | UAT | CUT | SUP | SUP | SUP
Customer Portal / San Francisco | PEND | PEND | BP | BP | BP | DEV | DEV | DEV | DEV | DEV | SIT | SIT | UAT | UAT | CUT
Data Warehouse Migration / Chicago | DEV | DEV | DEV | DEV | SIT | SIT | VAL | VAL | UAT | UAT | CUT | SUP | SUP | SUP | HC

## Project Demand
Projects | Plan Owner | Role | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11
Mobile Banking App / New York | Alice Johnson | Project Manager | 0.3 | 0.3 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.6 | 0.6 | 0.8 | 0.2 | 0.2 | 0.2
Mobile Banking App / New York | Bob Smith | Developer |  |  | 0.2 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.3 | 0.3 | 0.2
Mobile Banking App / New York | Carol White | QA Engineer |  |  | 0.1 | 0.3 | 0.3 | 0.3 | 0.5 | 1 | 1 | 0.8 | 0.8 | 0.4 | 0.1 | 0.1

## Project Capacity Gaps
Projects | Role | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11

## Project Assignments
Projects | Person | Role | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11
Mobile Banking App / New York | Alice Johnson | Project Manager | 0.3 | 0.3 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.6 | 0.6 | 0.8 | 0.2 | 0.2 | 0.2
Mobile Banking App / New York | Bob Smith | Developer |  |  | 0.2 | 0.8 | 0.8 | 0.8 | 0.8 | 0.5 | 0.5 | 0.3 | 0.3 | 0.2
Customer Portal / San Francisco | David Brown | UX Designer |  |  | 0.8 | 0.8 | 0.8 | 0.4 | 0.4 | 0.2 | 0.2 |  |  |  | 0.2 | 0.2

## Standard Allocations
Role | ProjType | PEND | BP | DEV | SIT | VAL | UAT | CUT | HC | SUP | IDLE | BLKOUT | GL
Project Manager | Mobile Application | 0.1 | 0.3 | 0.5 | 0.4 | 0.3 | 0.6 | 0.8 | 0.2 | 0.2
Developer | Mobile Application |  |  | 1 | 0.5 | 0.3 | 0.3 | 0.2
QA Engineer | Mobile Application |  | 0.1 | 0.3 | 1 | 0.8 | 0.8 | 0.4 | 0.1 | 0.1
Business Analyst | Mobile Application | 0.2 | 0.8 | 0.2 | 0.1 | 0.1 | 0.2 | 0.1
UX Designer | Mobile Application | 0.1 | BP: 0.8; DEV: 0.4; SIT: 0.1; UAT: 0.2

## Roles
Role | Plan Owner | CW Option | Reqd Data Access
Project Manager | Alice Johnson | Y | Full project access
Developer | Bob Smith | Y | Code repository
QA Engineer | Carol White | Y | Test environments
Business Analyst | Alice Johnson | N | Requirements docs
UX Designer | David Brown | N | Design tools
DevOps Engineer | Bob Smith | Y | Infrastructure
Data Analyst | Emma Wilson | N | Analytics platforms

## Roster
Person | Primary Role | Location | Contractor | Leave | Bubble | Notes | Description | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11
Alice Johnson | Project Manager | New York | N | N | N | Senior PM with 10 years experience | Leads mobile and web projects | 1 | 1 | 1 | 1 | 0.8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 1
Bob Smith | Developer | San Francisco | N | N | N | Full stack developer | Specializes in React and Node.js | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.8 | 1 | 1 | 1 | 1
Carol White | QA Engineer | Chicago | N | N | N | Test automation expert | Leads QA initiatives | 0.8 | 0.8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.6 | 0.6 | 1 | 1
David Brown | UX Designer | London | Y | N | N | Contract UX specialist | Mobile and web design | 1 | 1 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.4 | 0.4 | 0.4 | 0.4 | 0.8 | 0.8 | 1 | 1
Emma Wilson | Data Analyst | Berlin | N | N | N | Analytics and reporting | Business intelligence expert | 1 | 1 | 0.8 | 0.8 | 1 | 1 | 1 | 1 | 1 | 1 | 0.6 | 0.6 | 1 | 1 | 1

## Project Types
Type
Infrastructure
Mobile Application
Web Application
Data Analytics
Security
Research & Development
Integration

## Project Phases
Phase
PEND
BP
DEV
SIT
VAL
UAT
CUT
HC
SUP
IDLE
BLKOUT
GL