## Projects
Projects | Type | Inc. in Demand | Priority
Simple Web App / New York | Web Application | Y | 1
Mobile App / London | Mobile Application | Y | 2

## Project Roadmap
Projects | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11
Simple Web App / New York | BP | BP | DEV | DEV | DEV | SIT | UAT | CUT
Mobile App / London |  |  | BP | BP | DEV | DEV | DEV | SIT | UAT | CUT

## Project Demand
Projects | Plan Owner | Role | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11
Simple Web App / New York | John Smith | Project Manager | 0.5 | 0.5 | 0.3 | 0.3 | 0.3 | 0.4 | 0.6 | 0.8
Simple Web App / New York | Jane Doe | Developer |  |  | 1 | 1 | 1 | 0.5 | 0.2

## Project Capacity Gaps
Projects | Role | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11

## Project Assignments
Projects | Person | Role | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11
Simple Web App / New York | John Smith | Project Manager | 0.5 | 0.5 | 0.3 | 0.3 | 0.3 | 0.4 | 0.6 | 0.8
Simple Web App / New York | Jane Doe | Developer |  |  | 0.8 | 0.8 | 0.8 | 0.5 | 0.2

## Standard Allocations
Role | ProjType | PEND | BP | DEV | SIT | VAL | UAT | CUT | HC | SUP | IDLE | BLKOUT | GL
Project Manager | Web Application |  | 0.5 | 0.3 | 0.4 |  | 0.6 | 0.8 | 0.2 | 0.1
Developer | Web Application |  | DEV: 1; SIT: 0.5; UAT: 0.2; CUT: 0.1

## Roles
Role | Plan Owner | CW Option | Reqd Data Access
Project Manager | John Smith | Y | Full access
Developer | Jane Doe | Y | Code repository

## Roster
Person | Primary Role | Location | Contractor | Leave | Bubble | Notes | Description | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11
John Smith | Project Manager | New York | N | N | N | Senior project manager | Experienced PM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Jane Doe | Developer | New York | N | N | N | Full stack developer | React and Node.js expert | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Project Types
Type
Web Application
Mobile Application

## Project Phases
Phase
PEND
BP
DEV
SIT
VAL
UAT
CUT
HC
SUP
IDLE
BLKOUT
GL