## Projects
Projects | Type | Inc. in Demand | Priority
Enterprise Data Migration / New York | Infrastructure | Y | 1
Mobile Banking App / San Francisco | Mobile Application | Y | 2
Project with Very Long Name That Exceeds Normal Length Expectations And Tests Field Limits / Chicago | Web Application | Y | 1
Unicode Project 项目 プロジェクト проект / Tokyo | Research & Development | Y | 999
Special Characters!@#$%^&*() / London | Security | N | -5
Whitespace Project / Berlin | Integration | Y | 3
Duplicate Project Name / Mumbai | Data Analytics | Y | 1
Duplicate Project Name / Sydney | Mobile Application | N | 2
Project With Missing Data / Paris
/ Austin | Web Application | Y | 1

## Project Roadmap
Projects | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11
Enterprise Data Migration / New York | PEND | PEND | BP | BP | DEV | DEV | DEV | SIT | VAL | UAT | CUT | HC | SUP | SUP | IDLE
Mobile Banking App / San Francisco | BP |  | BP: DEV; BP: DEV; DEV: SIT; DEV: UAT; VAL: CUT; UAT: GL
Project with Very Long Name That Exceeds Normal Length Expectations And Tests Field Limits / Chicago | PEND | BP | DEV | SIT | VAL | UAT | CUT | HC | SUP | IDLE | BLKOUT | GL | SUP | IDLE | GL
Special Characters!@#$%^&*() / London | CUT | BP: UAT; DEV: SIT; SIT: DEV; VAL: BP

## Project Demand
Projects | Plan Owner | Role | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11
Enterprise Data Migration / New York | Alice Johnson | Project Manager | 0.5 | 0.5 | 0.8 | 0.8 | 1 | 1 | 1 | 0.8 | 0.6 | 0.9 | 1.2 | 0.3 | 0.2 | 0.2 | 0.1
Mobile Banking App / San Francisco | Bob Smith | Developer | 1.5 | 2 | 1.8 | 1.2 | 1 | 1.3 | 1.1 | 0.8 | 0.5 | 0.2
Unicode Project 项目 プロジェクト проект / Tokyo | Carol White | QA Engineer | 0.125 | 0.25 | 0.333 | 0.666 | 0.75 | 0.875 | 1.111 | 1.333 | 0.555 | 0.222
Special Characters!@#$%^&*() / London | David Brown | Business Analyst | 0 | -0.5 | 0 | 0.1 | 0 | -1 | 0 | 0.01 | 99.9 | 0
Project With Missing Data / Paris |  |  | 1 | 1 | 1

## Project Capacity Gaps
Projects | Role | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11

## Project Assignments
Projects | Person | Role | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11
Enterprise Data Migration / New York | Alice Johnson | Project Manager | 0.5 | 0.5 | 0.8 | 0.8 | 1 | 1 | 1 | 0.8 | 0.6 | 0.9
Mobile Banking App / San Francisco | Alice Johnson | Project Manager | 0.8 | 0.8 | 0.5 | 0.5 | 0.3
Unicode Project 项目 プロジェクト проект / Tokyo | Bob Smith | Developer | 0.6 | 0.6 | 0.8 | 0.8 | 1
Special Characters!@#$%^&*() / London | Bob Smith | Technical Lead | [5 empty] | 0.5 | 0.5 | 0.7 | 0.7 | 0.4
Project with Very Long Name That Exceeds Normal Length Expectations And Tests Field Limits / Chicago | Carol White | QA Engineer | 0.3 |  | 0.5 |  | 0.8 | 0.8 |  | 1 | 1
Project With Missing Data / Paris |  | Mystery Role | 1 | 1

## Standard Allocations
Role | ProjType | PEND | BP | DEV | SIT | VAL | UAT | CUT | HC | SUP | IDLE | BLKOUT | GL
Project Manager | Infrastructure | 0.2 | 0.8 | 0.5 | 0.6 | 0.7 | 0.8 | 1 | 0.8 | 0.3 | 0.1 |  | 0.5
Developer | Infrastructure |  | 0.1 | 1 | 0.8 | 0.5 | 0.3 | 0.5 | 0.2
QA Engineer | Mobile Application |  | 0.2 | 0.8 | 1.5 | 1.2 | 1.8 | 1 | 0.5 | 0.2
Business Analyst | Web Application | 0.333 | 0.666 | 0.125 | 0.25 | 0.125 | 0.5 | 0.75 | 0.125
Technical Lead | Security | 0.1 | 0.3 | 0.8 | 0.6 | 0.9 | 0.7 | 1 | 0.8 | 0.4 | 0.2 | 0 | 0.6
| Research & Development | 0.5 | BP: 0.5; DEV: 0.5

## Roles
Role | Plan Owner | CW Option | Reqd Data Access
Project Manager | Alice Johnson | Y | Full project access
Developer | Bob Smith | Y | Code repository and dev environments
QA Engineer | Carol White | Y | Test environments and bug tracking
Business Analyst | David Brown | N | Requirements and documentation
Technical Lead | Bob Smith | Y | Full technical access
Role with Very Long Name That Tests Field Length Limits and Database Constraints | Alice Johnson | Y | Extensive access requirements that span multiple systems and platforms
Unicode Role 角色 роль | Carol White | N | Unicode data access 访问 доступ
Special!@#$%^&*()Role | David Brown | Y | Special characters in access!
Whitespace Role | Alice Johnson | Y | Whitespace access
Bob Smith
Orphan Role | Non-existent Person | Y | Standard access

## Roster
Person | Primary Role | Location | Contractor | Leave | Bubble | Notes | Description | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42 | 24FW43 | 24FW44 | 24FW45 | 24FW46 | 24FW47 | 24FW48 | 24FW49 | 24FW50 | 24FW51 | 24FW52 | 25FW01 | 25FW02 | 25FW03 | 25FW04 | 25FW05 | 25FW06 | 25FW07 | 25FW08 | 25FW09 | 25FW10 | 25FW11
Alice Johnson | Project Manager | New York | N | N | N | Senior PM with 10+ years experience | Leads enterprise projects | 1 | 1 | 1 | 1 | 0.8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 1
Bob Smith | Developer | San Francisco | Y | N | N | Contract developer, flexible schedule | Full stack development specialist | 0.8 | 0.8 | 1 | 1 | 1 | 0.6 | 0.6 | 1 | 1 | 0.4 | 0.4 | 0.8 | 0.8 | 1 | 1
Carol White | QA Engineer | Chicago | N | Y | N | Extended medical leave from week 42 | Test automation expert | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.8 | 1
David Brown | Business Analyst | London | N | N | Y | Bubble resource for urgent requirements | Senior BA available for quick assignments | 0.2 | 0.2 | 0.8 | 0.8 | 0.3 | 0.3 | 1 | 1 | 0.1 | 0.1 | 0.6 | 0.6 | 0.4 | 0.4 | 0.2
Person with Very Long Name That Tests Database Field Limits and Application Handling | Technical Lead | Tokyo | N | N | N | Person with extremely long name for testing purposes and edge case handling | Technical leadership role with extensive experience across multiple domains | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Li Wei 李伟 | Developer | Singapore | N | N | N | Unicode name testing 测试 | International developer 国际开发者 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
O'Connor-Smith, Jr. | Project Manager | Dublin | N | N | N | Name with special characters: apostrophe, hyphen, comma | Tests special character handling | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Emma Wilson | Data Analyst | Berlin | N | N | N | Leading and trailing whitespace | Tests whitespace handling | 1 | 1 | 1 | 1 | 1
| QA Engineer | Austin | [5 empty] | 1 | 1
Test Person Extreme Values | Developer | Test City | N | N | N | Testing extreme availability values | Edge case testing | 0 | 0.01 | 10 | 999 | -5 | 1.999 | 0.001 | 100 | -0.5 | 1.5

## Project Types
Type
Infrastructure
Mobile Application
Web Application
Data Analytics
Security
Research & Development
Integration
Type with Very Long Name That Tests Field Length Limits
Unicode Type 类型 тип
Special!@#$%^&*()Type
Whitespace Type

## Project Phases
Phase
PEND
BP
DEV
SIT
VAL
UAT
CUT
HC
SUP
IDLE
BLKOUT
GL