## Project Types
Project Type
Infrastructure
Mobile Application
Web Application
Data Analytics
Research & Development

## Project Phases
Phase

## Roles
Role | Plan Owner | CW Option | Required Data Access
Project Manager | Alice Johnson | Y | Full project access
Developer | Bob Smith | Y | Code repository
QA Engineer | Carol White | Y | Test environments
Business Analyst | Alice Johnson | N | Requirements docs
UX Designer | David Brown | N | Design tools

## Roster
Person | Role | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42
Alice Johnson | Project Manager | 1 | 1 | 1 | 1 | 0.8 | 1 | 1
Bob Smith | Developer | 1 | 1 | 0.6 | 0.6 | 1 | 1 | 1
Carol White | QA Engineer | 0.8 | 0.8 | 1 | 1 | 1 | 0.5 | 0.5
David Brown | UX Designer | 1 | 1 | 1 | 0.4 | 0.4 | 1 | 1
Eve Davis | Business Analyst | 1 | 0.8 | 0.8 | 1 | 1 | 1 | 0.6

## Projects
Project/Site | Project Type | Inc. in Demand | Priority
Mobile Banking App / New York | Mobile Application | Y | 1
Customer Portal / San Francisco | Web Application | Y | 2
Data Warehouse Migration / Chicago | Infrastructure | Y | 1
Analytics Dashboard / London | Data Analytics | Y | 3

## Project Roadmap
Project/Site | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42
Mobile Banking App / New York | BP | REQ | REQ | DEV | DEV | SIT | UAT
Customer Portal / San Francisco | PEND | BP | BP | REQ | DEV | DEV | DEV
Data Warehouse Migration / Chicago | REQ | REQ | DEV | DEV | DEV | SIT | SIT
Analytics Dashboard / London | BP | BP | REQ | REQ | REQ | DEV | DEV

## Standard Allocations
Role | Project Type | PEND | BP | REQ | DEV | SIT | UAT | PROD
Project Manager | Mobile Application | 0.1 | 0.3 | 0.3 | 0.2 | 0.2 | 0.3 | 0.1
Developer | Mobile Application | 0 | 0 | 0.2 | 1 | 0.5 | 0.2 | 0
QA Engineer | Mobile Application | 0 | 0 | 0.1 | 0.3 | 1 | 0.8 | 0
Business Analyst | Mobile Application | 0.2 | 0.8 | 1 | 0.2 | 0.1 | 0.2 | 0
UX Designer | Mobile Application | 0 | 0.5 | 0.8 | 0.3 | 0 | 0.1 | 0

## Project Demand
Project/Site | Plan Owner | Role | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42
Mobile Banking App / New York | Alice Johnson | Project Manager | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.3
Mobile Banking App / New York | Bob Smith | Developer | 0 | 0.2 | 0.2 | 1 | 1 | 0.5 | 0.2
Mobile Banking App / New York | Carol White | QA Engineer | 0 | 0.1 | 0.1 | 0.3 | 0.3 | 1 | 0.8

## Project Capacity Gaps
Project/Site | Role | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42

## Project Assignments
Project/Site | Person | Role | 24FW36 | 24FW37 | 24FW38 | 24FW39 | 24FW40 | 24FW41 | 24FW42
Mobile Banking App / New York | Alice Johnson | Project Manager | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.3
Mobile Banking App / New York | Bob Smith | Developer | 0 | 0.2 | 0.2 | 0.8 | 0.8 | 0.5 | 0.2